## ProjectSchedule
QuickCheck for Whiley
Janice Chin
David Pearce & Lindsay Groves |  | Project Start: | 2018-03-19
|  | Display Week: | 1 |  |  | 2018-03-19 | [6 empty] | 2018-03-26 | [6 empty] | 2018-04-02 | [6 empty] | 2018-04-09 | [6 empty] | 2018-04-16 | [6 empty] | 2018-04-23 | [6 empty] | 2018-04-30 | [6 empty] | 2018-05-07 | [6 empty] | 2018-05-14 | [6 empty] | 2018-05-21 | [6 empty] | 2018-05-28 | [6 empty] | 2018-06-04 | [6 empty] | 2018-06-11 | [6 empty] | 2018-06-18 | [6 empty] | 2018-06-25 | [6 empty] | 2018-07-02 | [6 empty] | 2018-07-09 | [6 empty] | 2018-07-16 | [6 empty] | 2018-07-23 | [6 empty] | 2018-07-30 | [6 empty] | 2018-08-06 | [6 empty] | 2018-08-13 | [6 empty] | 2018-08-20 | [6 empty] | 2018-08-27 | [6 empty] | 2018-09-03 | [6 empty] | 2018-09-10 | [6 empty] | 2018-09-17 | [6 empty] | 2018-09-24 | [6 empty] | 2018-10-01 | [6 empty] | 2018-10-08 | [6 empty] | 2018-10-15 | [6 empty] | 2018-10-22 | [6 empty] | 2018-10-29 | [6 empty] | 2018-11-05 | [6 empty] | 2018-11-12
 | time axis 2018-03-19 to 2018-11-18
TASK | ASSIGNED TO | PROGRESS | START | END | DAYS | time axis 2018-03-19 to 2018-11-18
Trimester 1
Produce bibliography |  | 0% | 2018-03-19 | 2018-04-09 | 22
Produce project proposal |  | 0% | 2018-03-19 | 2018-04-09 | 22
Implement for primitive types: bool, byte, int, null |  | 0% | 2018-03-19 | 2018-04-16 | 29
Implement for complex types: void, array, union and records |  | 0% | 2018-04-16 | 2018-05-14 | 29
Produce preliminary report |  | 0% | 2018-05-14 | 2018-06-10
Extend automatic test generator |  | 0% | 2018-06-11 | 2018-07-02 | 22
Trimester 2
Produce slides for presentation of preliminary report |  | 0% | 2018-07-02 | 2018-07-09 | 8
Extend the automatic test generator |  | 0% | 2018-07-09 | 2018-07-30 | 22
Produce draft of final report |  | 0% | 2018-07-30 | 2018-09-15 | 48
Complete implementation |  | 0% | 2018-09-15 | 2018-10-05 | 21
Finalise final report |  | 0% | 2018-10-06 | 2018-10-21
Prepare slides for final presentation |  | 0% | 2018-10-22 | 2018-11-16 | 26
Insert new rows ABOVE this one
2018-01-13
Note on H6: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.